Areté Architecture

LTC-10 Budget Risk Map

Identify hidden project risks before they become budget resets.

| Primary decision | Before you trust an LTC project budget, have you identified the operational, compliance, infrastructure, phasing, and continuity risks that could reset the number later? |
| --- | --- |

How to use this worksheet: Complete this before approving an early project budget, financing assumption, scope direction, or value-engineering path. The goal is not to make the budget larger. The goal is to make the budget honest enough to manage.

1. Project Budget Context

| Project / facility | Budget stage | Project type | Primary decision date |
| --- | --- | --- | --- |
|  | □ ROM □ SD □ DD □ Permit □ Precon | □ Reno □ Expansion □ Repositioning □ Acquisition |  |
| Target scope | Target schedule / milestone | Current budget range | Known funding constraint |
| Decision owner | Clinical / operations input | Facilities input | Estimator / contractor input |

2. Hidden Budget Risks to Map

For each category, identify whether the risk is already priced, merely assumed, or still unknown. Unknown does not mean bad. Unknown but untracked is the problem.

| Risk category | What could reset the budget? | Current status | Who confirms? | Due date |
| --- | --- | --- | --- | --- |
| Known Scope | walls, rooms, finishes, systems, site work, and construction scope | □ Priced □ Assumed □ Unknown |  |  |
| Operational continuity | Beds offline, swing space, staff routes, med/meals/laundry disruption, resident/family communication | □ Priced □ Assumed □ Unknown |  |  |
| Compliance / survey / life safety | AHJ assumptions, egress, compartment/smoke strategy, survey-readiness expectations, door/hardware impacts | □ Priced □ Assumed □ Unknown |  |  |
| Infrastructure / MEP | Electrical capacity, HVAC comfort, hot water, generator/emergency power, low voltage/nurse call, controls | □ Priced □ Assumed □ Unknown |  |  |
| Phasing / temporary services | Temporary routes, temporary utilities, shutdowns, after-hours work, tie-ins, commissioning, inspections | □ Priced □ Assumed □ Unknown |  |  |
| Decision latency / scope drift | Late clinical decisions, delayed owner inputs, value-engineering loops, unclear alternates, added stakeholders | □ Priced □ Assumed □ Unknown |  |  |

3. Budget Risk Register

Use this register for the specific risks most likely to move the number. Keep the language practical: what happens, where it happens, what it costs if ignored, and what decision is needed next.

| Risk | Where it shows up | Budget impact | Likelihood | Mitigation / next test | Owner | GO? |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | □ Low □ Med □ High | □ Low □ Med □ High |  |  | □ GO □ Hold |
|  |  | □ Low □ Med □ High | □ Low □ Med □ High |  |  | □ GO □ Hold |
|  |  | □ Low □ Med □ High | □ Low □ Med □ High |  |  | □ GO □ Hold |
|  |  | □ Low □ Med □ High | □ Low □ Med □ High |  |  | □ GO □ Hold |
|  |  | □ Low □ Med □ High | □ Low □ Med □ High |  |  | □ GO □ Hold |
|  |  | □ Low □ Med □ High | □ Low □ Med □ High |  |  | □ GO □ Hold |
|  |  | □ Low □ Med □ High | □ Low □ Med □ High |  |  | □ GO □ Hold |
|  |  | □ Low □ Med □ High | □ Low □ Med □ High |  |  | □ GO □ Hold |

4. Contingency Logic: Generic vs. Risk-Based

| Contingency bucket | What it covers | Trigger for use | Decision owner |
| --- | --- | --- | --- |
| Design / scope uncertainty | Unresolved decisions that could change layout, systems, or phasing | Decision resolved differently than assumed |  |
| Existing conditions / infrastructure | Unknown capacity, hidden conditions, aging systems, tie-ins | Field verification or investigation changes assumptions |  |
| Operational continuity / phasing | Swing space, temporary services, off-hours work, staff/resident disruption controls | Phase plan requires added protection or sequencing |  |
| Compliance / AHJ / survey risk | Life safety, infection prevention, licensing/survey expectations, review comments | Authority or leadership confirmation changes path |  |

5. Budget Lock GO / NO-GO Gate

Use this gate before presenting a budget as reliable enough for financing, owner approval, major scope lock, or contractor pricing alignment.

☐ Operational continuity risks are named and either priced, mitigated, or intentionally accepted.

☐ Compliance, life safety, and survey-readiness assumptions have an assigned confirmation path.

☐ Infection prevention and occupied-renovation controls are identified where applicable.

☐ MEP and infrastructure risks have been reviewed with facilities and engineering input.

☐ Phasing, temporary services, shutdowns, and swing-space assumptions are visible in the budget.

☐ Contingency is tied to named risks, not only a generic percentage.

☐ Value-engineering options have been tested against operational consequences.

☐ Open risks have owners, due dates, and a decision path.

| Gate result | Use when | Next action |
| --- | --- | --- |
| GO | Known risks are priced, mitigated, or intentionally accepted. | Move forward with budget recommendation. |
| CONDITIONAL GO | A few risks remain open but have owners, due dates, and bounded impact. | Proceed only with assumptions clearly stated. |
| NO-GO | An open risk could reset scope, phasing, systems, schedule, or operations. | Do not trust the budget yet. Resolve the risk first. |

6. Final Budget Risk Statement

Write the statement leadership should understand before approving the budget.

The budget is reliable enough to move forward because...

The budget is still exposed because...

The lowest-cost effective next move is...

Areté Architecture | Predictability-first planning for long-term care projects