## TDM-MF_Pg1
MF-06 — Typology Decision Matrix (TDM-MF)
Purpose: Score Podium vs Wrap vs Stacked Flats using underwriting-relevant criteria. 1–5 (higher is better).
Project: |  |  |  | Date: 2026-03-17
A) Score each typology (1–5). Add notes where risk is high.
Criteria | Podium | Wrap | Stacked Flats | Notes / constraints | Owner action
Entitlement fit (height/setbacks/review risk)
Parking feasibility (ratio + type + constructability)
Cost predictability (structure + envelope complexity)
Schedule predictability (review loops + sequencing + long-leads)
Yield/net-to-gross potential (revenue capacity)
Civil impact (stormwater/grade/access/ROW)
Constructability logistics (staging/crane/site constraints)
Lease-up fit vs comps (product expectations)
TOTAL (sum of scores)
Decision rule: Highest score wins unless an If/Then trigger forces a reset decision.

## Triggers_Pg2
MF-06 — If/Then Triggers + Typology Workshop
Use these blunt triggers to prevent late typology resets and protect budget/schedule/yield.
A) If/Then Reset Triggers (circle if true)
□ If parking shifts to podium/structured → treat as a reset decision (re-price + re-schedule; often re-underwrite) □ If height/setbacks force 'perfect efficiency' → expect yield risk; validate net-to-gross early □ If civil/ROW scope is heavy → favor predictability over complexity; avoid fragile schemes □ If schedule window is tight → avoid options with high review iteration risk □ If unit mix/premiums depend on a feature the typology can't support → revisit product assumptions
B) 45-Minute Typology Decision Workshop (repeatable)
1) Confirm site constraints that drive typology (10 min) 2) Score the TDM-MF matrix together (20 min) 3) Apply triggers + name trade rules (10 min) 4) Decide typology + publish as source of truth (5 min)
Next episode (MF-07): Efficiency by Design — Unit Mix, Net-to-Gross, and Where Projects Quietly Lose Yield