Purpose: Use this worksheet before layout lock or construction phasing sign-off to test whether an occupied renovation can protect census, staffing reality, compliance, and resident/patient safety.

Rule: If a phase cannot preserve safe access, required services, clean/dirty control, staff coverage, and compliance continuity, do not lock the phase plan.

Project: ____________________    Facility/Program: ____________________    Date: ____________

Occupied?  Y / N    Target census to protect: ____________    Construction duration assumption: ____________

Participants: Admin/ED ____________  DON/Clinical ____________  Facilities ____________  GC/CM ____________  Other ____________

1) Continuity baseline: what must stay operational? Name the services and conditions that cannot fail while construction is active.

| Critical operation | Minimum service level | Owner / role responsible | If disrupted, what happens? |
| --- | --- | --- | --- |
| Beds / census |  |  |  |
| Meds |  |  |  |
| Meals / dining |  |  |  |
| Clean supply |  |  |  |
| Soiled / waste |  |  |  |
| Staff anchors |  |  |  |
| Visitor / service access |  |  |  |

2) Phasing inventory: define each phase before drawing routes Each phase should describe the work zone, beds/rooms affected, temporary routes, and decision risks.

| Phase | Work zone / scope | Beds or rooms offline | Temporary routes needed | Owner decision / risk |
| --- | --- | --- | --- | --- |
| 1 |  |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |
| 4 |  |  |  |  |
| 5 |  |  |  |  |
| 6 |  |  |  |  |

3) Census protection test A phase is not viable if it damages revenue or care continuity without an intentional mitigation plan.

| Phase | Target census impact | Beds offline / duration | Mitigation (swing rooms, sequencing, temporary service) | Status |
| --- | --- | --- | --- | --- |
| 1 |  |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |
| 4 |  |  |  |  |
| 5 |  |  |  |  |
| 6 |  |  |  |  |

4) Staff flow and resident/patient route test Trace routes for peak moments, not calm moments. Include med pass, meals, shift change, and emergency response.

| Route / movement | Normal route | Temporary route | Peak conflict? | Fix / mitigation |
| --- | --- | --- | --- | --- |
| Med pass |  |  |  |  |
| Meals / dining |  |  |  |  |
| Rounds |  |  |  |  |
| Admissions / discharge |  |  |  |  |
| Clean supply |  |  |  |  |
| Soiled / waste |  |  |  |  |
| Visitor access |  |  |  |  |
| Emergency response |  |  |  |  |

5) Compliance continuity check Confirm the phase maintains required life safety, infection prevention, and operational controls. Confirm requirements with the AHJ(s) and clinical/compliance leadership.

| [ ] | Temporary egress routes are defined, marked, and viable during peak moments. |
| --- | --- |
| [ ] | Fire/life-safety assumptions for each phase have a clear confirmation path with AHJ(s). |
| [ ] | Construction zones and clean care zones are separated conceptually. |
| [ ] | Dust/noise/odor and infection prevention controls are planned at phase level. |
| [ ] | Clean supply, soiled return, waste, and laundry flows do not create no-go crossings. |
| [ ] | Staff anchors remain usable, or temporary anchors are assigned and tested. |
| [ ] | Resident/patient movement is planned to protect safety, dignity, and care routines. |
| [ ] | Survey/compliance-sensitive areas are protected or intentionally relocated. |

6) Communication and decision cadence Occupied renovation needs a tighter operating rhythm because daily operations are part of the project risk.

| Cadence item | Owner / role | Frequency | What gets reviewed? | Notes |
| --- | --- | --- | --- | --- |
| Ops huddle |  |  |  |  |
| Resident/family comms |  |  |  |  |
| Staff route update |  |  |  |  |
| Phase readiness review |  |  |  |  |
| Risk register review |  |  |  |  |
| Go/No-go decision |  |  |  |  |

7) Phase GO / NO-GO gate Do not start or lock a phase until each item below is true.

| [ ] | Census impact is stated, accepted, and mitigated. |
| --- | --- |
| [ ] | Critical operations remain functional or have approved temporary solutions. |
| [ ] | Resident/patient, staff, visitor, service, clean, and soiled routes are defined. |
| [ ] | Life safety and infection prevention assumptions are confirmed or assigned for confirmation. |
| [ ] | Staff anchors and response routes work during peak moments. |
| [ ] | Communication plan is ready for staff, residents/families, and project team. |
| [ ] | Open risks that could change the phase are assigned with owner, due date, and decision path. |

Status:   [ ] GO for phase lock     [ ] NO-GO - revise phase plan before proceeding

Open risks / missing decisions (max 6):

__________________________________________________________________________________________

__________________________________________________________________________________________

__________________________________________________________________________________________

__________________________________________________________________________________________

__________________________________________________________________________________________

__________________________________________________________________________________________

Optimization statement: We are protecting ____________________ while allowing construction to proceed by ____________________.

__________________________________________________________________________________________

Next step: Carry unresolved items into a live phasing risk register and review them before each phase starts.