## EPM-MF_Pg1
MF-05 — Entitlement Path Map (EPM-MF)
Purpose: Map the real approval path + cycles, then baseline schedule truth and owners.
Project: |  |  |  | Date: 2026-03-17
A) Path Type (confirm with jurisdiction)
□ Ministerial □ Admin Review □ Design Review Board □ Hearing/Conditional Use □ Rezone/Variance
B) Map the Path (one line per step; include expected cycles)
# | Step | Expected cycle (weeks) | Dependencies | Owner | Notes
1 | Pre-app / intake meeting(s)
2 | Land use / design review step(s)
3 | Environmental review trigger check (if applicable)
4 | Building permit plan review — cycle 1
5 | Building permit plan review — cycle 2 (if needed)
6 | Civil/ROW permit path (often separate critical path)
7 | Utility approvals / service upgrades (if applicable)
8
9
C) Time Truth (what makes the schedule real)
Decision deadlines (owner/team): ________________________________ Resubmittal strategy: □ single coordinated response □ piecemeal Critical path hypothesis (circle): Architecture / Civil-ROW / Utility / Review Board Readiness rule: 'No submittal until package is complete.'

## TRR_Pg2
MF-05 — Time-Risk Register (TRR)
Log time risks that can add weeks/months. Assign mitigations + owners + due dates.
A) Time-Risk Register
# | Time risk | Trigger | Consequence | Mitigation action | Due
1
2
3
4
5
6
7
8
9
B) 90-Minute Path Mapping Workshop (repeatable)
1) Confirm path type + required steps (15 min) 2) Assign cycle-time assumptions per step (20 min) 3) Identify critical path + readiness rules (15 min) 4) Populate time-risk register + mitigations (30 min) 5) Publish as schedule source of truth (10 min)