# MF-09 — Design-to-Budget

Tool: Design-to-Budget Control Worksheet + Budget Variance Register

Default tool link: https://www.arete-architecture.design/mf-tools-trainings

## Purpose

Use this worksheet at every major option, estimate, and design phase gate. It keeps budget as a live design constraint so the team can protect the pro forma without relying on late-stage value engineering.

## Simple Rule

Design-to-budget means budget is managed while decisions are still flexible. Value engineering happens late when decisions are already expensive to unwind. The goal is not to cut; the goal is to choose, price, and trade early.

## A) Budget Baseline — define the scoreboard before reviewing design

| Baseline Item | Current target / assumption | Evidence / source | Owner / date |
| --- | --- | --- | --- |
| Hard-cost guardrail | $ __________ | Estimate / underwriting / lender assumption |  |
| Contingency / design reserve | _____% or $ __________ | Owner policy / risk profile |  |
| Escalation assumption | _____% through __________ | Estimator / market data |  |
| Pricing status | Concept / SD / DD / GMP / Bid | Estimator / GC / cost consultant |  |
| Known exclusions / allowances | List items not fully priced | Estimate qualifications |  |
| Decision tolerance band | Green: +/- ___% Yellow: ___% Red: ___% | Owner / underwriting |  |

## B) Major Cost Drivers — review before the team falls in love with an option

| Cost Driver | What to check early | Common budget risk | Trade idea before VE |
| --- | --- | --- | --- |
| Structure / typology | Podium, wrap, stacked flats, grid, transfers | Late structural change resets cost and schedule | Simplify geometry before cutting revenue drivers |
| Parking | Ratio, type, access, ramps, transitions | Parking solution drives structure and civil scope | Reduce optional scope before changing parking strategy |
| Envelope | Facade complexity, glazing, balconies, waterproofing | Small articulation adds repeated cost | Simplify repetition / details before cutting durability |
| MEP / utilities | Service capacity, shafts, equipment rooms, long-leads | Systems force area loss or upgrades | Coordinate early; carry explicit allowance if unknown |
| Site / civil / ROW | Stormwater, grading, frontage, access | Offsite work and civil permits add cost/time | Resolve red flags before advancing options |
| Amenities / BOH | Size, job, ops burden, displacement | Nice-to-have scope crowds out yield | Build / right-size / defer / skip |

# Design-to-Budget Option Review Scorecard

Use this during option reviews. The goal is to catch budget drift while the team still has choices, not after design decisions have hardened.

| Option / scope item | Design intent / value | Budget impact: Low / Med / High | Evidence status: Priced / Allowance / Unknown | Revenue / ops / schedule value | Decision: Protect / Simplify / Right-size / Defer / Price | Trade rule | Owner / date |
| --- | --- | --- | --- | --- | --- | --- | --- |

## Decision Outcome Definitions

| Outcome | Meaning | Use when... | Next action |
| --- | --- | --- | --- |
| Protect | Keep the scope because it supports revenue, operations, compliance, durability, or schedule. | Cutting it would harm the outcome. | Name what gets traded instead. |
| Simplify | Keep the intent, reduce complexity. | Cost comes from geometry, details, transitions, or repetition. | Redesign for simpler execution. |
| Right-size | Keep the function, reduce scope or area. | The idea is valid but oversized. | Set a target size or cap. |
| Defer | Preserve optionality without committing full scope now. | Evidence or timing is not strong enough. | Shell, phase, or revisit at a gate. |
| Price | Do not approve until cost/schedule impact is known. | The item is not priced or has major uncertainty. | Assign estimator/GC action. |

# C) Budget Variance Register

Use this register for any item that moves the budget, schedule, or value story. No variance should float without a cause, owner, trade rule, and next action.

| Variance item | Cause | Budget impact | Schedule impact | What it threatens | Decision owner | Trade rule / mitigation | Due date |
| --- | --- | --- | --- | --- | --- | --- | --- |

## D) Budget Gate Bands

| Band | Condition | Default action | Decision level |
| --- | --- | --- | --- |
| Green | Within agreed budget tolerance. | Document and continue. | Project team |
| Yellow | Approaching tolerance or driven by unpriced assumptions. | Price + schedule check; name trade rule. | Owner + architect + estimator |
| Red | Exceeds tolerance or threatens non-negotiable. | Pause; re-baseline or re-underwrite. | Owner decision |

# E) Design-to-Budget If/Then Rules

Use these rules during design reviews, estimate reviews, and owner decision meetings. The goal is to prevent late-stage value engineering by forcing price, trade, and ownership earlier.

| If... | Then... | Why it matters |
| --- | --- | --- |
| Scope is added without pricing | Do not approve it as baseline. Mark it “Price” and assign owner/date. | Prevents invisible budget drift. |
| Estimate moves into Yellow band | Run a price + schedule check and name trade rules. | Catches drift while options still exist. |
| Estimate moves into Red band | Pause and re-baseline the design, budget, or underwriting. | Prevents denial from becoming late VE. |
| A proposed cut touches revenue, operations, durability, or compliance | Do not call it VE. Treat it as a protected item and trade elsewhere. | Avoids value destruction. |
| A high-risk item is still unknown | Carry an explicit allowance/contingency or resolve it before advancing. | Makes risk visible instead of hidden. |
| A change affects multiple systems | Price it before approval and check schedule impact. | Small changes can have second-order effects. |

## F) 60-Minute Design-to-Budget Review

| Time | Agenda item |
| --- | --- |
| 10 min | Confirm budget baseline, contingency, exclusions, and pricing status. |
| 15 min | Review major cost drivers and estimate movement since the last gate. |
| 15 min | Classify scope items: Protect / Simplify / Right-size / Defer / Price. |
| 10 min | Update Budget Variance Register with owners, trade rules, and due dates. |
| 10 min | Confirm decisions, publish the budget source of truth, and tee up permit set readiness. |

## Next Episode Connection

MF-10 — Permit Set Readiness: The Drawing Quality Threshold That Protects Schedule. Once the project is aligned to budget, the next risk is submitting a permit set before the drawings are coordinated enough to protect review time.