MULTIFAMILY TOOL | MF-11

GMP Scope Confidence Test

+ Pricing Risk Register

Core decision: Is this GMP based on coordinated, priceable scope — or is it carrying unresolved risk through assumptions, allowances, exclusions, and missing information?

How to use this tool

Use this worksheet before accepting or relying on a GMP. The goal is not to prove the price is perfect. The goal is to test whether the contractor had enough coordinated information to make reasonable assumptions and whether the remaining risk is visible, owned, and governed.

Key rule: The drawings do not need to be perfect. The GMP does need to make the remaining uncertainty visible.

Gate decision

| Outcome | Use when... |
| --- | --- |
| Ready to Price | Scope is coordinated enough for reasonable assumptions. Major risks are priced, documented, or explicitly owned. |
| Price With Known Risks | A pricing deadline is real, but remaining risks are limited, visible, assigned, and carried in the register. |
| Not Ready — Resolve Before GMP | Unresolved gaps are likely to hide major scope, distort pricing, or become future change orders. |

Recommended meeting output

• A gate decision: Ready to Price, Price With Known Risks, or Not Ready.

• A completed scope confidence score across the five tests.

• A pricing risk register with owner, mitigation, due date, and decision status.

• A short list of items that must be clarified before the GMP can be relied on.

Part 1 — GMP Scope Confidence Test

Score each test as Ready, Risk, or Not Ready. Do not debate vague comfort. Name what information supports the score and what must be resolved before the number is relied on.

| # | Test | What must be true | Score / evidence |
| --- | --- | --- | --- |
| 1 | Drawing coordination | Architecture, structural, civil, MEP, fire protection, accessibility, and specifications reconcile well enough for a contractor to price scope without guessing between contradictions. | Ready / Risk / Not Ready Evidence/gap: ____________________ |
| 2 | Site information | Survey, existing conditions, utilities, geotech, grades, access, ROW, easements, and civil constraints are reliable enough to prevent scope surprises. | Ready / Risk / Not Ready Evidence/gap: ____________________ |
| 3 | Assumptions quality | Contractor assumptions are specific, tied to drawings or narratives, and acceptable to the owner. Vague assumptions are resolved or carried as risks. | Ready / Risk / Not Ready Evidence/gap: ____________________ |

| # | Test | What must be true | Score / evidence |
| --- | --- | --- | --- |
| 4 | Allowances + exclusions | Allowances and exclusions are limited, justified, owner-visible, and not carrying major unpriced scope that should be defined. | Ready / Risk / Not Ready Evidence/gap: ____________________ |
| 5 | Change-order exposure | Likely future change-order triggers are named, assigned, and either priced, mitigated, excluded knowingly, or resolved before GMP acceptance. | Ready / Risk / Not Ready Evidence/gap: ____________________ |

Pass/fail logic: One Not Ready item can block reliance on the GMP if it could hide major scope or materially change cost, schedule, or constructability.

Owner / PM accountability questions

• What scope did the contractor have to assume because the drawings did not define it?

• Which allowances are carrying real scope risk rather than minor finish or quantity uncertainty?

• Which exclusions would become owner cost if the scope is later required?

• What site, survey, civil, utility, or existing-condition information is still unverified?

• What would most likely become a change order after GMP acceptance?

Part 2 — Pricing Risk Register

Use this register to turn hidden risk into governed risk. Every material assumption, allowance, exclusion, missing input, or coordination gap should have an owner and a due date.

| # | Risk item | Where it may be hiding + consequence | Owner / due / status | Mitigation |
| --- | --- | --- | --- | --- |
| 1 | Survey / site geometry discrepancy | Faulty or unverified survey; building location, setback, grades, or foundation relationship is uncertain. Consequence: Potential redesign, field conflict, foundation change, delay. | Owner: ________ Due: ________ Status: ________ | Mitigation / trade rule: ____________________ |
| 2 | Civil / utility scope gap | Stormwater, frontage, utility relocation, service capacity, or easement scope not fully defined. Consequence: Unpriced site work or AHJ-driven scope after GMP. | Owner: ________ Due: ________ Status: ________ | Mitigation / trade rule: ____________________ |
| 3 | Structural transfer / podium assumption | Transfer condition, grid, opening, or podium interface priced from incomplete coordination. Consequence: Major structural premium or constructability issue. | Owner: ________ Due: ________ Status: ________ | Mitigation / trade rule: ____________________ |

| # | Risk item | Where it may be hiding + consequence | Owner / due / status | Mitigation |
| --- | --- | --- | --- | --- |
| 4 | MEP service / equipment assumption | Service size, equipment room, shaft, riser, routing, or long-lead equipment not fully reconciled. Consequence: Cost increase, area impact, or schedule exposure. | Owner: ________ Due: ________ Status: ________ | Mitigation / trade rule: ____________________ |
| 5 | Allowance carrying real scope | Allowance covers undefined scope instead of minor quantity/specification uncertainty. Consequence: False budget certainty; later owner cost. | Owner: ________ Due: ________ Status: ________ | Mitigation / trade rule: ____________________ |
| 6 | Exclusion that may be required | Excluded scope may still be required by permit, AHJ, lender, utility, or operations need. Consequence: Future change order or delayed approval. | Owner: ________ Due: ________ Status: ________ | Mitigation / trade rule: ____________________ |

Risk status legend

| Status | Meaning |
| --- | --- |
| Open | Risk is known but not resolved or priced. |
| Priced | Risk is carried in the GMP, allowance, contingency, or alternate. |
| Excluded knowingly | Owner understands the exclusion and accepts how it will be handled later. |
| Resolved | Information was clarified and the risk no longer materially affects the GMP. |

Part 3 — Trade Rules Before Accepting the GMP

Use these rules to decide whether a risk can remain in the GMP package or must be resolved before the price is relied on.

| Condition | Trade rule |
| --- | --- |
| If the drawings conflict... | Do not let the contractor price both interpretations silently. Select the basis of pricing or carry a visible risk. |
| If an allowance carries major scope... | Do not treat it as budget certainty. Define the scope, set a range, or mark it as a pricing risk. |
| If an exclusion may be required... | Name who pays if it returns and whether it must be resolved before acceptance. |
| If site information is unreliable... | Price with a risk register only if the impact range is visible and acceptable. |
| If the change-order pathway is obvious... | Do not wait for construction. Decide whether to price, mitigate, redesign, or accept the exposure. |

45-minute GMP scope confidence meeting

| Time | Action |
| --- | --- |
| 5 min | Confirm pricing milestone, GMP basis, and what drawings/specs/narratives the contractor used. |
| 10 min | Review the five scope confidence tests and mark Ready / Risk / Not Ready. |
| 10 min | Review assumptions, allowances, exclusions, and alternates that could hide major scope. |
| 10 min | Populate the Pricing Risk Register with owner, mitigation, and due date. |
| 5 min | Make the gate decision: Ready to Price, Price With Known Risks, or Not Ready. |
| 5 min | Publish the pricing source of truth and unresolved items before GMP acceptance. |