30-Day Friction Pilot Plan

SESSION 1  ·  Run your Top 3 fixes through Baseline → Quick Win → Standardize → Re-measure

Where this fits in your workflow.  You’ve walked the building with the 30-Minute Audit Scorecard. You’ve triaged your findings with the Friction-to-FTE Calculator. The two or three highest-dollar findings are now in front of you. This plan is how you run them. Each fix gets its own page so the work can be distributed — DON owns Fix #1, Maintenance owns Fix #2, and so on.

Why a pilot, not a checklist.  A checklist creates activity. A pilot creates a case study. The difference matters because the next conversation — with ownership, with a board, with a lender — is built on what you can prove changed. Without a baseline, you cannot claim a win. Without a re-measure, you cannot ask for the next thing. This plan exists so your Day 30 conversation sounds like “here’s what we measured, here’s what changed, here’s what’s next” — not “we tried some things and it felt better.”

THE 4-STAGE CYCLE

| 1. BASELINE | 2. QUICK WIN | 3. STANDARDIZE | 4. RE-MEASURE |
| --- | --- | --- | --- |
| Days 1–3 Capture the number you have today — minutes lost, incidents, observations. No baseline, no case study. | Days 4–14 Implement the no-capex or low-capex countermeasure. One fix at a time. Visible. Owned. | Days 15–25 Make it stick. SOP, training, visual cue, accountability. Without this stage, the fix decays in 60 days. | Days 26–30 Same measure as baseline. The delta is the headline. Real win, partial, or no — you call it honestly. |

THREE MEETINGS THAT KEEP THE PILOT ALIVE

| WHEN | MEETING | AGENDA (15 minutes max) |
| --- | --- | --- |
| Day 1 | Pilot Kickoff | Walk the audit Top 3. Confirm owners. Lock baseline measure for each. Lock dates for the next two meetings. |
| Day 14 | Mid-Pilot Check-In | “What got implemented? What’s blocked?” Resolve barriers fast. Don’t wait until Day 30 to discover a fix never started. |
| Day 30 | Review + Decide | Re-measure delta for each fix. Decide: hold the gain, re-audit the station, escalate to LOW-CAPEX, or move to next priority. |

Put all three on the calendar before you leave the kickoff. Pilots that don’t have a Day 30 booked never reach Day 30.

FIX #1 OF 3 · one full life cycle: Baseline → Quick Win → Standardize → Re-measure

THE FIX

| What we’re fixing | __________________________________________________________ |
| --- | --- |
| Friction type | ☐ TIME ☐ COGNITIVE ☐ SAFETY |
| Fix tier | ☐ NO-CAPEX ☐ LOW-CAPEX ☐ CAPEX |
| Owner | ______________________ Deadline: ____________ |

STAGE 1   BASELINE  ·  Days 1–3

| What we’re measuring | __________________________________________________________ |
| --- | --- |
| How we’ll measure it | ☐ Timed observation ☐ Incident log ☐ Time study ☐ QAPI report ☐ Other |
| Baseline number | ______________________ Captured by: ______________ Date: _________ |

STAGE 2   QUICK WIN  ·  Days 4–14

| Countermeasure | __________________________________________________________ |
| --- | --- |
| Implementation steps | 1. ________________________________________________________ by ______ 2. ________________________________________________________ by ______ 3. ________________________________________________________ by ______ |
| Resources / cost | __________________________________________________________ |
| Status | ☐ Started ☐ Completed Date completed: ____________ |

STAGE 3   STANDARDIZE  ·  Days 15–25

| SOP / policy update | ☐ N/A ☐ Drafted ☐ Approved Document: ______________________ |
| --- | --- |
| Training delivered | ☐ N/A ☐ Yes Audience: ____________________ Date: ______ |
| Visual cue installed | ☐ N/A ☐ Yes What: _______________________________________ |
| Sustain owner | ______________________ Review cadence: ☐ Weekly ☐ Monthly ☐ Quarterly |

STAGE 4   RE-MEASURE  ·  Days 26–30

| New number (same measure as baseline) | ______________________ Captured by: ______________ Date: _________ |
| --- | --- |
| Delta | Baseline _______ minus current _______ = _______ |
| Was the win real? | ☐ Yes — hold the gain ☐ Partial — iterate ☐ No — escalate or re-design |
| What’s next? | ☐ Hold the gain ☐ Re-audit this station ☐ Escalate to LOW-CAPEX/CAPEX ☐ Move to next priority |

FIX #2 OF 3 · one full life cycle: Baseline → Quick Win → Standardize → Re-measure

THE FIX

| What we’re fixing | __________________________________________________________ |
| --- | --- |
| Friction type | ☐ TIME ☐ COGNITIVE ☐ SAFETY |
| Fix tier | ☐ NO-CAPEX ☐ LOW-CAPEX ☐ CAPEX |
| Owner | ______________________ Deadline: ____________ |

STAGE 1   BASELINE  ·  Days 1–3

| What we’re measuring | __________________________________________________________ |
| --- | --- |
| How we’ll measure it | ☐ Timed observation ☐ Incident log ☐ Time study ☐ QAPI report ☐ Other |
| Baseline number | ______________________ Captured by: ______________ Date: _________ |

STAGE 2   QUICK WIN  ·  Days 4–14

| Countermeasure | __________________________________________________________ |
| --- | --- |
| Implementation steps | 1. ________________________________________________________ by ______ 2. ________________________________________________________ by ______ 3. ________________________________________________________ by ______ |
| Resources / cost | __________________________________________________________ |
| Status | ☐ Started ☐ Completed Date completed: ____________ |

STAGE 3   STANDARDIZE  ·  Days 15–25

| SOP / policy update | ☐ N/A ☐ Drafted ☐ Approved Document: ______________________ |
| --- | --- |
| Training delivered | ☐ N/A ☐ Yes Audience: ____________________ Date: ______ |
| Visual cue installed | ☐ N/A ☐ Yes What: _______________________________________ |
| Sustain owner | ______________________ Review cadence: ☐ Weekly ☐ Monthly ☐ Quarterly |

STAGE 4   RE-MEASURE  ·  Days 26–30

| New number (same measure as baseline) | ______________________ Captured by: ______________ Date: _________ |
| --- | --- |
| Delta | Baseline _______ minus current _______ = _______ |
| Was the win real? | ☐ Yes — hold the gain ☐ Partial — iterate ☐ No — escalate or re-design |
| What’s next? | ☐ Hold the gain ☐ Re-audit this station ☐ Escalate to LOW-CAPEX/CAPEX ☐ Move to next priority |

FIX #3 OF 3 · one full life cycle: Baseline → Quick Win → Standardize → Re-measure

THE FIX

| What we’re fixing | __________________________________________________________ |
| --- | --- |
| Friction type | ☐ TIME ☐ COGNITIVE ☐ SAFETY |
| Fix tier | ☐ NO-CAPEX ☐ LOW-CAPEX ☐ CAPEX |
| Owner | ______________________ Deadline: ____________ |

STAGE 1   BASELINE  ·  Days 1–3

| What we’re measuring | __________________________________________________________ |
| --- | --- |
| How we’ll measure it | ☐ Timed observation ☐ Incident log ☐ Time study ☐ QAPI report ☐ Other |
| Baseline number | ______________________ Captured by: ______________ Date: _________ |

STAGE 2   QUICK WIN  ·  Days 4–14

| Countermeasure | __________________________________________________________ |
| --- | --- |
| Implementation steps | 1. ________________________________________________________ by ______ 2. ________________________________________________________ by ______ 3. ________________________________________________________ by ______ |
| Resources / cost | __________________________________________________________ |
| Status | ☐ Started ☐ Completed Date completed: ____________ |

STAGE 3   STANDARDIZE  ·  Days 15–25

| SOP / policy update | ☐ N/A ☐ Drafted ☐ Approved Document: ______________________ |
| --- | --- |
| Training delivered | ☐ N/A ☐ Yes Audience: ____________________ Date: ______ |
| Visual cue installed | ☐ N/A ☐ Yes What: _______________________________________ |
| Sustain owner | ______________________ Review cadence: ☐ Weekly ☐ Monthly ☐ Quarterly |

STAGE 4   RE-MEASURE  ·  Days 26–30

| New number (same measure as baseline) | ______________________ Captured by: ______________ Date: _________ |
| --- | --- |
| Delta | Baseline _______ minus current _______ = _______ |
| Was the win real? | ☐ Yes — hold the gain ☐ Partial — iterate ☐ No — escalate or re-design |
| What’s next? | ☐ Hold the gain ☐ Re-audit this station ☐ Escalate to LOW-CAPEX/CAPEX ☐ Move to next priority |

DAY 30 REVIEW

Translate the pilot into the language ownership uses

This is the conversation that funds the next ask. Don’t walk into the next ownership meeting with a story. Walk in with the table below filled out. The numbers anchor the story — not the other way around.

BEFORE / AFTER  —  ALL 3 FIXES

| # | FIX | BASELINE | DAY 30 | DELTA |
| --- | --- | --- | --- | --- |
| 1 | ________________________ | __________ | __________ | __________ |
| 2 | ________________________ | __________ | __________ | __________ |
| 3 | ________________________ | __________ | __________ | __________ |

TRANSLATE THE DELTA

Pick one or two of these reframes. The right one depends on who you’re talking to.

| FOR THIS AUDIENCE | USE THIS FRAME |
| --- | --- |
| Owner / Board | “We ran a 30-day pilot on three friction items. We saved ____ minutes per shift, which equals ____ FTE annualized. Here’s the next ask.” |
| CFO / Controller | “Delta of ____ hours/year against a labor cost of $____. Annualized recovery: $____. Cost of the fix: $____. Payback: ____ months.” |
| DON / Charge Staff | “We gave back ____ hours/week to resident-facing care — not paperwork, not hunting. Here’s how we’ll hold the gain.” |
| Surveyor / QAPI | “We identified an environmental contributor, baselined it, intervened, and re-measured. Here’s the delta. Here’s the standard work that holds it.” |

WHAT WE LEARNED  (the part operators forget to capture)

| What worked better than expected | ____________________________________________ ____________________________________________ |
| --- | --- |
| What didn’t work — and why | ____________________________________________ ____________________________________________ |
| What surprised us | ____________________________________________ ____________________________________________ |
| Top 3 for the NEXT pilot | 1. ________________________________________________________ 2. ________________________________________________________ 3. ________________________________________________________ |