## DoD_Charter_Pg1
Definition of Done Charter (DoD-C)
MF-02 Multifamily ¦ Budget • Schedule • Yield • 3 Non-Negotiables
Project Info
Project: | [7 empty] | Date: |  |  |  |  | Version:
Owner / Sponsor: | [7 empty] | Architect PM: |  |  |  |  | Estimator:
Use at kickoff or reset. Reference in every SD/DD option review and every change conversation.
A) Budget Definition of Done | [8 empty] | B) Schedule Definition of Done
Hard-cost guardrail (target): | [8 empty] | Key milestone dates (baseline):
Budget assumptions (check + annotate): | [8 empty] | Permit submit:
☐ | Construction type assumed: | [7 empty] | Permit approval target:
☐ | Parking type assumed: |  |  |  | Surface |  |  |  | Start construction:
☐ | Envelope complexity limit (plain words): | [7 empty] | First move-in / first revenue:
☐ | MEP complexity limit (plain words): | [7 empty] | Stabilization target:
☐ | Finish level baseline (plain words):
Schedule triggers (set now):
Tolerance bands (set now): | [8 empty] | Slip of |  | days on a key milestone → Level 2: Price + Schedule
| Green: | ± | % | No escalation / no reset |  |  |  |  | Slip of |  | days on First move-in → Level 3: Re-underwrite / reset
| Yellow: | ± | % | Requires Level 2: Price + Schedule
| Red: | > | % | Level 3: Re-underwrite / reset
C) Yield Definition of Done
Targets:
| Unit count target: |  |  |  |  | Unit mix target (counts): | Studio: |  |  | 1BR: | 2BR: | 3BR:
Efficiency / yield guardrail (plain language):
Yield triggers (set now):
• Change of ± |  |  |  | units → Level 3 (re-underwrite / reset)
• Mix shift that changes revenue model → Level 3
• Efficiency drop beyond |  |  |  | (define your metric) → Level 3
Tip: If you can’t state the yield guardrail in one sentence, it’s not ready to govern decisions.

## DoD_Charter_Pg2
Definition of Done Charter (DoD-C)
MF-02 Multifamily ¦ Non-Negotiables • Trade Rules • Change Ladder
D) The 3 Non-Negotiables (pick exactly three)
Rule: If a proposal touches a non-negotiable → pause + decide (Level 3).
Non-Negotiable |  |  | Why underwriting cares (money/time/risk)
#1
#2
#3
E) Trade Rules (what we trade first) |  |  |  |  | F) Change Trigger Ladder (governance)
When pressure hits, we trade in this order:
[5 empty] | Level 0 — Document: | No measurable impact. Log it.
1)
[5 empty] | Level 1 — Evaluate: | Architect checks feasibility + second-order impacts.
2)
[5 empty] | Level 2 — Price + Schedule: | Estimator + scheduler quantify delta.
3)
[5 empty] | Level 3 — Re-underwrite / reset: | Touches non-negotiables or breaks DoD bands.
Examples: Trade optional amenity SF before unit mix; trade finish upgrades before parking type.
3 Non-Negotiables Test (1-minute check for any proposed change)
1) Does the change touch Budget, Schedule, or Yield targets?
• No → Level 0/1 (document or evaluate)
• Yes → go to #2
2) Does it move us outside tolerance bands or hit a trigger?
• No → Level 2 (price + schedule) with an explicit trade rule
• Yes → go to #3
3) Does it touch any of the 3 non-negotiables?
• No → Level 2 with explicit trade rule
• Yes → Level 3 (pause + decide; re-underwrite/reset)
Sign-off (names):
Owner: |  |  |  | Architect: |  |  | Estimator: