## SSG-MF_Pg1
MF-04 — Site Spend Gate Checklist (SSG-MF)
Purpose: Confirm the site is design-ready before spending real schematic design dollars. Result = GO / GO-WITH-CONDITIONS / NO-GO.
Project: |  |  |  | Date: 2026-03-17
Owner/Dev Lead: |  |  |  | Version:
A) Inputs required BEFORE SD options multiply (check + note constraints)
# | Item | Status (Known / In Progress / Unknown) | Key constraints / notes | Owner | Due date
1 | Survey/topo + easements/ROW (ALTA if applicable)
2 | Zoning + overlays + height/setback realities + review trigger
3 | Critical areas screening (wetlands/streams/steep slope + buffers)
4 | Utilities: location + capacity + upgrade/offsite risk
5 | Stormwater approach: infiltration vs detention/conveyance
6 | Geotech baseline: borings plan + groundwater/soil risk
7 | Access/fire: turning, hydrants, grade/ADA feasibility
8 | Frontage/ROW improvements: sidewalk/curb/trees/signals
9 | Title constraints: CC&Rs/shared access/encroachments
10 | Constructability logistics: staging/laydown/crane/haul routes
B) Spend Gate Result (circle one and list conditions if needed)
GO |  | GO-WITH-CONDITIONS |  | NO-GO
Conditions / deal-reset risks (if any):

## SSG-MF_Pg2
SSG-MF — Red-Flag Register + Spend Gate Meeting Outputs
Use this page to log deal-reset risks and assign next actions with due dates.
C) Red-Flag Register (log anything that could reset massing / parking / typology / unit count)
# | Red flag | What it could break | When it must be known | Best next action | Due
1
2
3
4
5
6
7
8
D) 30-Minute Spend Gate Meeting Agenda (repeatable)
1) Confirm site inputs status (5 min) 2) Review red flags + what they break (10 min) 3) Decide GO / GO-WITH-CONDITIONS / NO-GO (5 min) 4) Assign next actions + due dates (7 min) 5) Publish checklist + register as the site source of truth (3 min)