MF-10 — Permit Set Readiness Gate

Drawing Quality Threshold Checklist + Review-Cycle Risk Register

Purpose: Use this gate before permit submittal to decide whether the drawing set is ready, risky, or not ready. The owner does not need to coordinate every drawing; this tool helps the owner/PM hold the design team accountable for the quality threshold that protects review time.

## A) Submittal Decision Gate

Select one outcome at the end of the readiness meeting. Do not treat “submitted” as progress if the set is likely to buy preventable review cycles.

| Decision | Use when... | Required action | Owner / Due date |
| --- | --- | --- | --- |
| Ready to Submit | Core coordination gaps are resolved; known risks are documented and acceptable. | Submit with one coordinated package and a reviewer-friendly response strategy. |  |
| Submit With Known Risks | A deadline is real, but limited risks remain that are unlikely to reset the set. | Document risks, owners, and how each will be handled during review. |  |
| Not Ready — Resolve First | Unresolved gaps are likely to create preventable comments, resubmittal cycles, or redesign. | Pause submittal; resolve the readiness gaps before sending. |  |

## B) Drawing Quality Threshold Checklist — Part 1

Mark each threshold as Ready / Risk / Not Ready. A “Not Ready” item should name an owner, a required fix, and a date before submittal proceeds.

| Threshold area | What must be true before submittal | Status | Owner | Resolve by |
| --- | --- | --- | --- | --- |
| Sheet set completeness | Sheet index, legends, abbreviations, code sheets, plans, elevations, sections, details, schedules, and consultant sheets are present and coordinated. | Ready / Risk / Not Ready |  |  |
| Code + life safety story | Occupancy, construction type, egress, fire ratings, accessibility, sprinkler/alarm assumptions, and fire separation strategy are internally consistent. | Ready / Risk / Not Ready |  |  |
| Civil / site alignment | Site plan, grading, utilities, stormwater, fire access, ROW/frontage work, and architectural entries/levels align across disciplines. | Ready / Risk / Not Ready |  |  |
| Architectural coordination | Grids, dimensions, levels, wall types, unit plans, stairs/elevators, shafts, assemblies, and key details do not conflict across sheets. | Ready / Risk / Not Ready |  |  |
| Structural coordination | Structural grids, framing assumptions, foundations, transfers, podium conditions, shafts, openings, and architectural geometry are coordinated. | Ready / Risk / Not Ready |  |  |

## B) Drawing Quality Threshold Checklist — Part 2

Continue the same threshold test. The point is not perfection; the point is preventing avoidable reviewer confusion and rework.

| Threshold area | What must be true before submittal | Status | Owner | Resolve by |
| --- | --- | --- | --- | --- |
| MEP / FP coordination | Shafts, risers, equipment rooms, service routes, penetrations, utility assumptions, and fire protection/life-safety dependencies are shown enough to review. | Ready / Risk / Not Ready |  |  |
| Accessibility + fair housing | Accessible routes, unit requirements, parking/loading, common areas, grades, thresholds, and clearances are coordinated and checkable. | Ready / Risk / Not Ready |  |  |
| Owner decisions frozen | Unit mix, amenities, major materials, scope exclusions, alternates, and known budget decisions are frozen or clearly documented. | Ready / Risk / Not Ready |  |  |
| Cross-references + details | Keynotes, callouts, section/detail references, schedules, and specifications point to the right information and do not send reviewers searching. | Ready / Risk / Not Ready |  |  |
| Review package discipline | The package is internally checked; known risks are logged; submittal narrative explains the project clearly and anticipates reviewer questions. | Ready / Risk / Not Ready |  |  |

## C) Review-Cycle Risk Register

Use this register for anything that may trigger preventable reviewer comments, resubmittal cycles, consultant rework, or schedule drift.

| Risk / gap | Likely reviewer question | Consequence | Owner | Fix / mitigation | Due |
| --- | --- | --- | --- | --- | --- |
| Civil/architectural elevations do not align |  | Extra review comments; revised site/building coordination |  |  |  |
| Fire access or hydrant assumption unclear |  | Life-safety comments; possible site redesign |  |  |  |
| Wall ratings / shaft ratings inconsistent |  | Correction cycle; consultant rework |  |  |  |
| Accessibility route or unit requirements unclear |  | Reviewer friction; rework in plans/schedules |  |  |  |
| MEP equipment locations not coordinated |  | Plan review comments; area or layout revisions |  |  |  |
| Owner scope change still unresolved |  | Permit set becomes moving target |  |  |  |
| Budget-driven alternate unclear |  | Confusing review package; re-issue risk |  |  |  |

## D) 45-Minute Permit Set Readiness Meeting

| Time | Agenda item | Output |
| --- | --- | --- |
| 5 min | Confirm deadline and submittal strategy | Decision deadline and submittal path are explicit. |
| 10 min | Review drawing quality threshold checklist | Ready/Risk/Not Ready status assigned. |
| 10 min | Review consultant coordination gaps | Civil, structural, MEP/FP, accessibility, and code issues identified. |
| 10 min | Populate review-cycle risk register | Risks have owner, fix, and due date. |
| 5 min | Make gate decision | Ready / Submit With Known Risks / Not Ready. |
| 5 min | Publish source of truth | Final readiness decision and required actions distributed. |

## E) Owner Questions That Create Accountability

- What are the top three coordination risks that could create review comments?

- Which consultant sheets still require reconciliation before submittal?

- What known risks are we submitting with, and why are they acceptable?

- What reviewer questions are we anticipating and answering in the package?

- What issues, if unresolved, should stop submittal?